## Summary
Yellow cell values should be entered specific to this project
Light gray cells are either N/A or reference yellow cells and usually do not need to be edited
Dark gray cells are calculated, but can be overriden
Important summations
Input
Quantity | Items |  | Quantity | Items
100 | Existing pages of documentation for review |  | 2000000 | Total project budget
1 | Existing systems being updated or replaced |  | 125 | BA blended hourly cost
52 | Stakeholders |  | Standard | Type of project
25 | Interfacing Systems - small systems |  | 8 | Number of developers
2 | Interfacing Systems - medium systems |  | No | Is your team remote?
1 | Interfacing Systems - large systems |  | 56 | Project duration? (weeks)
15 | Process Flows |  | 28 | Requirements work duration? (weeks)
2 | BDDs
20 | Screens
20 | Reports
Summary Total Effort Comparison
|  | % of total project | Ratio of dev to BAs | Activity based
| Number of BAs | 2.1429 | 1.3333 | 1.1041 | *Excludes time off
| BA budget for requirements work | 300000 | 187000 | 155000
| BA budget for project duration | 600000 | 373000 | 309000
Estimates
Category | Activity | Hours by Category | Hours | Minutes per unit | Units | Minutes | Notes
Project Start and Management |  | 207
| Requirements plans |  | 19 | 1140 | N/A | 1140
| Status reporting |  | 119 | 255 | 28 | 7140 | Uses requirements project duration above
| Requirements architecture |  | 15.1667 | 910 | N/A | 910
| Project kick-off |  | 20 | 1200 | N/A | 1200
| Functions/Features organization |  | 16 | 960 | N/A | 960
| Traceability Links |  | 10.5 | 1 | 630 | 630
| Existing documentation review |  | 3.3333 | 2 | 100 | 200
| Existing systems review |  | 4 | 240 | 1 | 240
Model Requirements - People |  | 393.25
| Process Flows |  | 164 | 656 | 15 | 9840
| Org Charts |  | 7.5 | 450 | 1 | 450
| User Stories |  | 216 | 216 | 60 | 12960
| Decision Trees |  | 5.75 | 230 | 1.5 | 345
Model Requirements - System |  | 310.8333
| System Context Diagrams |  | 12.5 | 750 | 1 | 750
| System Interface Models - small systems |  | 125 | 300 | 25 | 7500
| System Interface Models - medium systems |  | 33.3333 | 1000 | 2 | 2000
| System Interface Models - large systems |  | 40 | 2400 | 1 | 2400
| Display-Action-Response Tables |  | 100 | 300 | 20 | 6000 | Uses number of screens, above
Model Requirements - Data |  | 325.5
| Business Data Diagrams |  | 7 | 210 | 2 | 420
| Data Flow Diagrams |  | 49.5 | 495 | 6 | 2970
| Data Dictionaries |  | 60 | 180 | 20 | 3600
| State Tables |  | 4.5 | 270 | 1 | 270
| State Diagrams |  | 4.5 | 270 | 1 | 270
| Report Tables |  | 200 | 600 | 20 | 12000
Total Effort
| Requirements Work | 1236.5833
| Remote Team Buffer add-on | 0
BA estimate based on activities
| Hours of work with buffer | 1236.5833
| Number of BAs for the Requirements Work | 1.1041 | Assumes input requirements duration, excludes time off
| BA cost for requirements work | 154572.9167 | Assumes input cost
| BA cost for entire project | 309145.8333 | Assumes input project duration and cost |  |  |  |  | BA Requirements effort cost | 154572.9167
BA estimate as ratio of Developers to BAs
| Developers per BA Standard | 6
| Developers per BA COTS | 3
| Number of BAs for entire project | 1.3333
| BA cost for requirements work | 186666.6667 | Assumes input requirements duration and cost
| BA cost for entire project | 373333.3333 | Assumes input project duration and cost
BA estimate as % of total budget
| Total budget | 2000000
| Percent of budget allocated to requirements | 15% | 15% is industry standard
| BA budget for requirements work | 300000
| Number of BAs for the Requirements Work | 2.1429 | Assumes input requirements duration and cost
| BA budget for project duration | 600000 | Assumes input project duration and cost

## Assumptions
Yellow cell values should be entered specific to this project
Light gray cells are either N/A or reference yellow cells and usually do not need to be edited
Dark gray cells are calculated, but can be overriden
Estimated Model counts and Assumptions
| Model | Quantity | Estimate based on |  |  | Assumptions (* indicates assumption varies based on project size-- Small, Medium, or Large) | #
| User Stories | 60 | Process Flow |  |  | Steps in a Process Flow | 20
| Decision Trees | 1.5 | Process Flow |  |  | User Stories per Process Flow | 4
| DFDs | 6 | BDDs |  |  | Decision Trees per Process Flow | 0.1
| Data Dictionaries | 20 | BDDs |  |  | Decision points in a Decision Tree | 10
| State Tables | 1 | BDDs |  |  | Data objects in a BDD | 10
| State Diagrams | 1 | BDDs |  |  | Total objects in a DFD | 15
| Requirements | 210 | Process Flow |  |  | State objects to define per BDD | 0.5
| Business Rules | 630 | Process Flow |  |  | States in a state model | 10
| Number of traces | 630 | Process Flow |  |  | DFDs per BDD | 3
[6 empty] | People in an Org Chart (S:10, M:30, L:50)* | 50
|  | # |  |  |  | Systems in a System Context Diagram (S:10, M:30, L:50)* | 50
[6 empty] | Elements in a Screen | 15
[6 empty] | Elements in a Report | 20
[6 empty] | Requirements per step in a Process Flow | 0.7
[6 empty] | Business rules per requirement | 3
[6 empty] | Requirements per Process Flow | 14
[6 empty] | Business rules per Process Flow | 42
[6 empty] | Unique requirements per User Story | 4
[6 empty] | Traces per requirement (to Process Flow, Screen, User Story) | 3
Detailed Calculations for each activity
Category | Activity | Section Subtotal (minutes) | Total Minutes | Estimate per Element (minutes) | Number of Elements | Notes | Suggested Time - Low (minutes) | Suggested Time - High (minutes)
Project Start and Management
| Requirements plans | 1140
| Create detailed requirements plans |  | 720 | 720 | N/A | Burndowns for budget and activities | 480 | 960
| Create burndowns |  | 180 | 180 | N/A | Burndowns for budget and activities | 120 | 240
| Complete the methodolgy checklist |  | 240 | 240 | N/A | Use checklists to build plan | 120 | 360
| Status reporting | 255
| Create a weekly status report |  | 60 | 60 | N/A | Time per week for status reporting | 15 | 90
| Weekly status meeting |  | 60 | 60 | N/A | Time per week for status meetings | 15 | 120
| Core Team meetings |  | 75 | 75 | N/A | Time per week for core team meetings | 30 | 90
| Defect review meetings |  | 60 | 60 | N/A | Time per week for defect review meetings | 30 | 120
| Requirements architecture | 910
| Define Requirements Architecture |  | 700 | 700 | N/A | Setup architecture objects and where the artifacts live | 400 | 1000
| Setup team repository (SP and RM tools) |  | 210 | 210 | N/A | Setup sharepoint, requirements tools, etc. | 180 | 240
| Kicking off project | 1200
| Project kickoff meetings |  | 360 | 360 | N/A | Prep and have meeting | 240 | 480
| Project familiarization |  | 240 | 240 | N/A | Basic project introduction | 90 | 360
| Complete Business Problems and Objectives |  | 600 | 600 | N/A | Elicit and document business objectives | 120 | 1200
| Organizing Functions/Features | 960
| Identify all major buckets of functionality |  | 480 | 480 | N/A | Identify features, functions, modules, etc. | 240 | 1000
| Determine how to organize work |  | 480 | 480 | N/A | Make decisions about how to organize all of the work | 120 | 1200
| Existing documentation | 2
| Review existing documentation |  | 2 | 2 | N/A | Review a page in a document | 0.5 | 5
| Existing systems | 240
| Get trained in existing or new systems |  | 240 | 240 | N/A | Get up to speed on existing system | 30 | 480
| Traceability Matrix | 1
| Traceability Matrix creation |  | 0.5 | 0.5 | N/A | Time to link | 0.25 | 3
| Traceability Matrix analysis |  | 0.5 | 0.5 | N/A | Time per link to find issues or gaps | 0.5 | 3
Model Requirements - People
| Org Charts | 450
| Org Chart elicitation |  | 50 | 1 | 50 | People within an org chart | 0 | 5
| Org Chart creation |  | 100 | 2 | 50 |  | 1 | 5
| Org Chart internal review |  | 50 | 1 | 50 |  | 1 | 3
| Org Chart customer review |  | 100 | 2 | 50 |  | 1 | 3
| Evaluate org charts against stakeholder lists |  | 150 | 3 | 50 |  | 1 | 5
| Process Flows | 656
| Elicitation prep, meet, follow-up |  | 120 | 120 | N/A | Sessions breakdown (30 prep, 60 meet, 30 follow-up) | 60 | 180
| Process Flow creation |  | 60 | 3 | 20 | Steps within a process flow | 1 | 6
| Process Flow internal review |  | 60 | 3 | 20 |  | 1 | 6
| Process Flow customer review |  | 80 | 4 | 20 |  | 1 | 10
| Derive Requirements and business rules |  | 112 | 2 | 56 | Requirements and business rules per process flow | 1 | 6
| Review and Update derived requirements |  | 224 | 4 | 56 |  | 1 | 10
| User Stories | 216
| User Story elicitation |  | 60 | 60 | N/A | Session breakdown (20 prep, 30 meet, 10 follow-up) | 30 | 120
| User Story creation |  | 20 | 20 | N/A |  | 10 | 45
| User Story internal review |  | 10 | 10 | N/A |  | 5 | 30
| User Story customer review |  | 30 | 30 | N/A |  | 10 | 60
| Derive Requirements and business rules |  | 32 | 2 | 16 | Requirements and business rules per user story | 1 | 6
| Review and Update derived requirements |  | 64 | 4 | 16 |  | 1 | 10
| Decision Trees | 230
| Decision Tree creation |  | 10 | 1 | 10 | Decision points within a decision tree | 1 | 10
| Decision Tree internal review |  | 10 | 1 | 10 |  | 1 | 5
| Decision Tree customer review |  | 30 | 3 | 10 |  | 1 | 10
| Derive Requirements and business rules |  | 60 | 2 | 30 | Business rules per decision tree | 1 | 6
| Review and Update derived requirements |  | 120 | 4 | 30 |  | 1 | 10
Model Requirements - System
| System Context Diagram | 750
| System Context Diagram elicitation |  | 150 | 3 | 50 |  | 0 | 6
| System Context Diagram creation |  | 150 | 3 | 50 | Systems within a context diagram | 1 | 10
| System Context Diagram internal review |  | 150 | 3 | 50 |  | 1 | 6
| System Context Diagram customer review |  | 300 | 6 | 50 |  | 1 | 10
| Small System Interface Models |  | 300 | 300 | N/A | Small custom system, few data pieces | 40 | 400
| Medium System Interface Models |  | 1000 | 1000 | N/A |  | 400 | 2000
| Large System Interface Models |  | 2400 | 2400 | N/A | Lots of data is passed, lots of interface points | 2000 | 4000
| DAR models | 300
| Wireframe creation |  | 60 | 4 | 15 | Elements within a screen | 0 | 10
| Wireframe internal review |  | 30 | 2 | 15 |  | 1 | 10
| Wireframe customer review |  | 60 | 4 | 15 |  | 1 | 20
| Display-Action-Response creation |  | 60 | 4 | 15 | Elements within a screen | 2 | 10
| Display-Action-Response internal review |  | 30 | 2 | 15 |  | 1 | 5
| Display-Action-Response customer review |  | 60 | 4 | 15 |  | 2 | 10
Model Requirements - Data
| Business Data Diagrams | 210
| Business Data Diagram elicitation |  | 60 | 60 | N/A | Session breakdown (20 prep, 30 meet, 10 follow-up) | 30 | 120
| Business Data Diagram creation |  | 60 | 6 | 10 | Objects within a business data diagram | 3 | 10
| Business Data Diagram internal review |  | 30 | 3 | 10 |  | 1 | 6
| Business Data Diagram customer review |  | 60 | 6 | 10 |  | 3 | 10
| Data Flow Diagrams | 495
| Data Flow Diagram creation |  | 90 | 6 | 15 | Objects within a data flow diagram | 3 | 10
| Data Flow Diagram internal review |  | 45 | 3 | 15 |  | 1 | 6
| Data Flow Diagram customer review |  | 90 | 6 | 15 |  | 3 | 10
| Derive Requirements and business rules |  | 90 | 2 | 45 | Business rules per DFD | 1 | 6
| Review and Update derived requirements |  | 180 | 4 | 45 |  | 1 | 10
| Data Dictionaries | 180
| Data Dictionary creation |  | 60 | 6 | 10 | Elements within a data dictionary | 3 | 9
| Data Dictionary internal review |  | 60 | 6 | 10 |  | 1 | 10
| Data Dictionary customer review |  | 60 | 6 | 10 |  | 1 | 10
| State Tables | 270
| State Table creation |  | 60 | 6 | 10 | States in a state table | 3 | 9
| State Table internal review |  | 30 | 3 | 10 |  | 1 | 5
| State Table customer review |  | 30 | 3 | 10 |  | 1 | 5
| Derive Requirements and business rules |  | 60 | 2 | 30 | Business rules per state table | 1 | 6
| Review and Update derived requirements |  | 90 | 3 | 30 |  | 1 | 10
| State Diagrams | 270
| State Diagram creation |  | 60 | 6 | 10 | States in a state diagram | 3 | 9
| State Diagram internal review |  | 30 | 3 | 10 |  | 1 | 5
| State Diagram customer review |  | 30 | 3 | 10 |  | 1 | 5
| Derive Requirements and business rules |  | 60 | 2 | 30 | Business rules per state diagram | 1 | 6
| Review and Update derived requirements |  | 90 | 3 | 30 |  | 1 | 10
| Report Tables | 600
| Report Table elicitation |  | 120 | 120 | N/A | Sessions breakdown (30 prep, 60 meet, 30 follow-up) | 60 | 180
| Report Table creation |  | 120 | 6 | 20 | Elements in a report | 3 | 10
| Report Table internal review |  | 120 | 6 | 20 |  | 1 | 5
| Report Table customer review |  | 240 | 12 | 20 |  | 3 | 20

## Instructions
Quick Start
| 1 | Access the Summary worksheet. Fill in the yellow cells with relevant numbers.
| 2 | Access the Assumptions worksheet. Review the standards in the yellow cells. Change them if necessary.
| 3 | Return to the summary worksheet and review your totals.
Detailed Information
Color Coding Key
Yellow cell values should be entered specific to this project
Light gray cells are either N/A or reference yellow cells and usually do not need to be edited
Dark gray cells are calculated, but can be overriden
Important summations
Summary Worksheet
The Summary worksheet contains project assumptions, effort on a model-by model basis, and total effort.
Input Section
You must fill in the left column of yellow cells. Filling in the the column of yellow cells to the right is optional.
Project duration is the total expected length of the project. It is used to estimate how many weeks beyond the requirements effort are needed, and is used in calculating BA support needed for that timeframe. It does not have to be entered.
Requirements Work Duration is the total expected length of time spent on requirements in a project. It is used to estimate time for status reporting (since it is throughout this period). And it is used for estimating how many BAs are needed based on the total work and desired duration.
Total project budget is only used as another means of estimating how much should be spent on the requirements effort.
Number of developers and type of project are used to estimate how many BAs are needed on the project in general.
Estimates Section
This section provides estimates on a model-by-model basis, based on the Inputs section and the Assumptions worksheet.
Total Effort Section
The calculations tell you the total work under "Total Effort" based on pre-set formulas.
The total BA count is calculated based on the duration of requirements work input at the top.
If you specified in the inputs that the team is remote, then a 10% buffer is added to the hours for ineffective time use.
The number of BAs you can estimate needing based on number of developers is at the bottom of the summary tab.
The budget for BAs can be estimated as a percent of the total project.
The estimated BA cost based on the requirements work total is calculated as well.
The BA support cost through the rest of the project is calculated based on number of BAs needed per number of developers.
Assumptions Worksheet
The Assumption worksheet contains the assumptions which are used determine the average effort to complete each model or requirements artifact.
You do not have to change any of the assumption, but you may.
The yellow cells are all standards, but can be altered.
Estimated Model counts and Assumptions Section
At the top left, the number of models produced is calculated.
Detailed Calculations for each activity Section
Details below are the estimates to create each individual model or element.
Suggested Time - Low and - High are numbers you can use to decide on the value used in column E.
Element is any object or sub object used in the estimate. Element could be a use case, a step in a use case, a process flow, a button in a screen, or a link in a screen.